## CHHS Demo Plan
Sno. | Phase/Activity | Start Date | End Date | STATUS | Date of Completion | Owner | Rahul B | Amit S | Brijesh | Manoj Marar | Ajit Pal | Vishal | Vivek | Veenus | Naveen
1 | INITIATION PHASE | 2016-05-24 | 2016-05-25
| VALIDATE INITIATION REVIEW CHECKLIST |  |  | COMPLETED | 2016-05-24 | Rahul B, Amit Sikka | 2
| PROVISION DEV SERVER VM |  |  | COMPLETED | 2016-05-24 | Brijesh |  |  | 4
| PROVISION QA SERVER VM |  |  | COMPLETED | 2016-05-24 | Brijesh |  |  | 4
| SETUP DEV SERVER - S/W INSTALLATION |  |  | COMPLETED | 2016-05-24 | Amit Sharma |  | 4
| SETUP QA SERVER - S/W INSTALLATION |  |  | COMPLETED | 2016-05-24 | Amit Sharma |  | 4
| SETUP GITHUB PROJECT REPOSITORY - UI & API |  |  | COMPLETED | 2016-05-24 | Amit Sharma |  | 4 | 2
| SETUP REQUIREMENTS MANAGEMENT TOOL - REDMINE with Agile Backlog and GIT integration |  |  | On HOLD |  | Brijesh, Manoj Marar |  |  | 4 | 6
| PROVISION BUILD SERVER VM |  |  | COMPLETED | 2016-05-25 | Brijesh |  |  | 4
| SETUP JENKINS |  |  | COMPLETED | 2016-05-26 | Amit Sharma |  | 4
| GENERATE PIN & ALLOCATE RESOURCE |  |  | COMPLETED | 2016-05-24 | Rahul B | 1
| DEFINE CODING STD |  |  | NOT STARTED |  | Rahul B , Amit Sharma |  | 1
| DEFINE CHECKIN GUIDELINE |  |  | NOT STARTED |  | Rahul B, Amit Sharma |  | 1
| DEFINE BACKLOG |  |  | COMPLETED | 2016-05-25 | Rahul B | 4
| DEFINE SPRINT SCHEDULE |  |  | COMPLETED | 2016-05-25 | Rahul B | 4
2 | DESIGN PHASE | 2016-05-25 | 2016-05-27
| PREPARE TECHNICAL DESIGN SPEC |  |  | IN PROGRESS |  | Rahul B , Amit Sharma |  | 6
| REVIEW TECHNICAL DESIGN SPEC |  |  | NOT STARTED |  | Vishal | [5 empty] | 2
| DB DESIGN |  |  | IN PROGRESS |  | Manoj Marar |  |  |  | 2
| DB DESIGN REVIEW |  |  | NOT STARTED |  | Vishal, Amit Sharma |  | 1 |  |  |  | 1
| SETUP DB - CREATE SCRIPTS |  |  | NOT STARTED |  | Manoj Marar |  |  |  | 2
| CREATE BRD |  |  | COMPLETED | 2016-05-27 | Veenus | [7 empty] | 6
| REVIEW BRD |  |  | COMPLETED | 2016-05-27 | Rahul B,Amit Sikka | 1
| GROOM BACKLOG STORIES - UI |  |  | COMPLETED | 2016-05-27 | Veenus | [7 empty] | 8
| GROOM BACKLOG Stories - API |  |  | COMPLETED | 2016-05-27 | Rahul B , Amit Sharma | 2 | 4
| APPROVE BACKLOG |  |  | COMPLETED |  | Amit Sikka | 1
| DESIGN PROTOTYPE |  |  | IN PROGRESS |  | Naveen | [8 empty] | 24
| REVIEW PROTOTYPE |  |  | NOT STARTED |  | Rahul B ,Amit Sikka | 2
| SETUP AUTOMATION TEST FRAMEWORK |  |  | NOT STARTED |  | Vivek | [6 empty] | 4
| CREATE TEST PLAN |  |  | NOT STARTED |  | Vivek | [6 empty] | 2
| SETUP INTEGRATION TESTS - Integration with Jenkins |  |  | NOT STARTED |  | Amit Sharma, Vishal |  | 4 |  |  |  | 4
| SETUP BUILD Server - AUTO BUILD SCRIPTS AUTO DEPLOY SCRIPTS |  |  | IN PROGRESS |  | Amit Sharma, Vishal, Brijesh |  | 4 | 2 |  |  | 4
| UI DESIGN FREEZE |  |  |  |  | Amit Sikka
| TECHNICAL DESIGN FREEZE |  |  |  |  | Vishal , Amit Sikka
3 | SPRINT PLANNING | 2016-05-26 | 2016-05-27
| ALLOCATE BACKLOG ITEMS |  |  | COMPLETED | 2016-05-27 | Rahul B | 1
4 | SPRINT EXECUTION
| SPRINT 1 | 2016-05-28 | 2016-05-31
| DEVELOP_WORK_ITEM |  |  |  |  | Amit Sharma, Naveen, Ajit | 8 | 32 | 8 | 2 | 32 | 4 | 32 |  | 8
| CREATE JUNITS |  |  |  |  | Amit Sharma
| CREATE UI Unit Test Case |  |  |  |  | Ajit
| PERFORM UNIT TESTING |  |  |  |  | Amit Sharma, Ajit
| PERFORM CODE REVIEW |  |  |  |  | Vishal
| CREATE AUTOMATION SYSTEM TEST CASE |  |  |  |  | Vivek
| CODE CHECKIN |  |  |  |  | Amit Sharma, Ajit
| AUTO BUILD |  |  |  |  | Brijesh
| DEPLOY TO QA SERVER |  |  |  |  | Brijesh
| SPRINT REVIEW |  |  |  |  | Rahul B, Amit Sikka
SPRINT CLOSE
| SPRINT 2 | 2016-06-01 | 2016-06-04
| DEVELOP_WORK_ITEM |  |  |  |  | Amit Sharma, Naveen, Ajit | 8 | 32 | 8 | 2 | 32 | 4 | 32 |  | 8
| CREATE JUNITS |  |  |  |  | Amit Sharma
| CREATE UI Unit Test Case |  |  |  |  | Ajit
| PERFORM CODE REVIEW |  |  |  |  | Vishal
| PERFORM UNIT TESTING |  |  |  |  | Amit Sharma, Ajit
| CREATE AUTOMATION SYSTEM TEST CASE |  |  |  |  | Vivek
| EXECUTE AUTOMATION SYSTEM TEST CASE |  |  |  |  | Vivek
| CODE CHECKIN |  |  |  |  | Amit Sharma, Ajit
| BUILD |  |  |  |  | Brijesh
| DEPLOY TO QA SERVER |  |  |  |  | Brijesh
| SPRINT REVIEW |  |  |  |  | Rahul B, Amit Sikka
SPRINT CLOSE
5 | STABILIZATION
| REGRESSION TEST CASE EXECUTION | 2016-06-05 | 2016-06-05 |  |  | Vivek |  |  |  |  | 8 |  | 8
| BUG FIXIN | 2016-06-05 | 2016-06-05 |  |  | Amit Sharma, Ajit, Rahul B, Vishal | 2 | 8 |  |  |  |  | 2
CODE FREEZE
6 | UAT | 2016-06-06 | 2016-06-06 |  |  | Rahul B , Vaibhav, Amit Sikka | 2 |  |  |  |  | 2
7 | BUG FIXING | 2016-06-06 | 2016-06-06 |  |  | Amit Sharma , Ajit |  | 8 |  |  | 8
8 | Documentation | 2016-06-05 | 2016-06-07 |  |  | Veenus | [7 empty] | 24
9 | GO NOGO | 2016-06-06 | 2016-06-06 |  |  | Amit Sikka
10 | CODE FREEZE GITHUB REPOSITORY | 2016-06-07 | 2016-06-07 |  |  | Amit Sharma, Vishal | 2 | 8 | 8 |  |  | 4
486