## Project Initiation Checklist
Proposal and Contract Preparation Check-list
Project Type |  | Pursuit- PreSales Initiative
Project Name: |  | CHHS Prototype Development
S.No. | Checkpoints |  | Status | Remarks
1 | Is RFP available? |  | Yes
2 | Has the RFP been analyzed for technical feasibility? |  | Yes
3 | Have the commercial facts been analyzed in the RFP? |  | NA | This is for a new business opportunity
4 | Is the scope of work, referred in the RFP, analyzed ? |  | Yes
5 | Has the capability to execute the project been analyzed? |  | Yes
4 | Has the adequacy of 'Scope of Work' (SOW) been checked ? |  | Yes | Working Prototype Development
5 | If SOW requires more information, has the client been approached to provide required information? |  | NA | This is for a new business opportunity
6 | Are the assumptions documented and revalidated with the contract / SOW? |  | NA | Not Applicable at this stage
7 | Is any productivity/ Development tools been identified (if Yes) has the requirement for the same been documented ? |  | Yes
8 | Is there a need for acquiring new technology / Tool? if Yes has the technology practice team been contacted for the same |  | No
9 | Has all the Open / Optional items of scope been closed/ resolved from the client |  | NA | This is for a new business opportunity
10 | Is the estimation speadsheet available and is standard template been used for calculating efforts estimation |  | Yes
11 | Has the review been performed by more than one person for all contract and precontract documents? |  | Yes | RFP is reviewed
12 | In case of major deviation in scope from original scope and contracted scope, has the re-estimation been done and the deviations been highlighted & reviewed |  | NA | Not Applicable
13 | Has the effort in man-hrs has been derived from function points or WBS |  | Yes | WBS
14 | Has the source and rationale of using this estimated data been documented e.g. the history data used for deriving the productivity figures |  | Yes
15 | Have quotations been procured for bought-out items/ services |  | NA
16 | Is the scope of bought-out items/ services mapped with the SOW of vendor and contract |  | NA
17 | What is the basis of calculating estimated cost? If it is similar past projects check the history data. |  | NA
18 | Does the cost estimate include other costs like travel, communication, procurement of hardware and system software including COTS, Translation, Miscellaneous and cost on human resource ? |  | NA
19 | Has the Technical Proposal been prepared and last version is available |  | NA
20 | Does the contract SOW and Commercial Proposal SOW are mapped |  | NA | This is for a new business opportunity
21 | Has the Proposal, Efforts and Cost estimates been reviewed by the GDH/ DH
22 | Have the review comments been documented along with technical and commercial risks. Check if the review comments have been incoporated |  | NA
23 | Does the project proposal containing Technical and Commercial Proposal been submitted to the client |  | No
24 | Have Client comments been analysed and resolved and incorporated in the proposal |  | NA
25 | Acceptance is obtained from the client on the proposal/ SOW or Contract refers to the SOW submitted or SOW is part of contract |  | NA