## CHHS Demo Plan
Sno. | Phase/Activity | Start Date | End Date | STATUS | Date of Completion | Owner
1 | INITIATION PHASE | 2016-05-24 | 2016-05-25
| VALIDATE INITIATION REVIEW CHECKLIST |  |  | COMPLETED | 2016-05-24 | Rahul B, Amit Sikka
| PROVISION DEV SERVER VM |  |  | COMPLETED | 2016-05-24 | Brijesh
| PROVISION QA SERVER VM |  |  | COMPLETED | 2016-05-24 | Brijesh
| SETUP DEV SERVER - S/W INSTALLATION |  |  | COMPLETED | 2016-05-24 | Amit Sharma
| SETUP QA SERVER - S/W INSTALLATION |  |  | COMPLETED | 2016-05-24 | Amit Sharma
| SETUP GITHUB PROJECT REPOSITORY - UI & API |  |  | COMPLETED | 2016-05-24 | Amit Sharma
| SETUP REQUIREMENTS MANAGEMENT TOOL - REDMINE with Agile Backlog and GIT integration |  |  | On HOLD |  | Brijesh, Manoj Marar
| PROVISION BUILD SERVER VM |  |  | COMPLETED | 2016-05-25 | Brijesh
| SETUP JENKINS |  |  | COMPLETED | 2016-05-26 | Amit Sharma
| GENERATE PIN & ALLOCATE RESOURCE |  |  | COMPLETED | 2016-05-24 | Rahul B
| DEFINE CODING STD |  |  | COMPLETED |  | Rahul B , Amit Sharma
| DEFINE CHECKIN GUIDELINE |  |  | COMPLETED |  | Rahul B, Amit Sharma
| DEFINE BACKLOG |  |  | COMPLETED | 2016-05-25 | Rahul B
| DEFINE SPRINT SCHEDULE |  |  | COMPLETED | 2016-05-25 | Rahul B
2 | DESIGN PHASE | 2016-05-25 | 2016-05-27
| PREPARE TECHNICAL DESIGN SPEC |  |  | COMPLETED | 2016-05-29 | Rahul B , Amit Sharma
| REVIEW TECHNICAL DESIGN SPEC |  |  | COMPLETED | 2016-05-31 | Vishal
| DB DESIGN |  |  | COMPLETED | 2016-05-29 | Manoj Marar
| DB DESIGN REVIEW |  |  | COMPLETED | 2016-05-29 | Vishal, Amit Sharma
| SETUP DB - CREATE SCRIPTS |  |  | COMPLETED | 2016-05-29 | Manoj Marar
| CREATE BRD |  |  | COMPLETED | 2016-05-27 | Veenus
| REVIEW BRD |  |  | COMPLETED | 2016-05-27 | Rahul B,Amit Sikka
| GROOM BACKLOG STORIES - UI |  |  | COMPLETED | 2016-05-27 | Veenus
| GROOM BACKLOG Stories - API |  |  | COMPLETED | 2016-05-27 | Rahul B , Amit Sharma
| APPROVE BACKLOG |  |  | COMPLETED | 2016-05-26 | Amit Sikka
| DESIGN PROTOTYPE |  |  | COMPLETED | 2016-05-28 | Naveen
| REVIEW PROTOTYPE |  |  | COMPLETED | 2016-06-02 | Rahul B ,Amit Sikka
| SETUP AUTOMATION TEST FRAMEWORK |  |  | COMPLETED | 2016-05-31 | Vivek
| CREATE TEST PLAN |  |  | COMPLETED | 2016-05-31 | Vivek
| SETUP INTEGRATION TESTS - Integration with Jenkins |  |  | COMPLETED | 2016-06-01 | Amit Sharma, Vishal
| SETUP BUILD Server - AUTO BUILD SCRIPTS AUTO DEPLOY SCRIPTS |  |  | COMPLETED | 2016-06-02 | Amit Sharma, Vishal, Brijesh
| UI DESIGN FREEZE |  |  | COMPLETED |  | Amit Sikka
| TECHNICAL DESIGN FREEZE |  |  | COMPLETED |  | Vishal , Amit Sikka
3 | SPRINT PLANNING | 2016-05-26 | 2016-05-27
| ALLOCATE BACKLOG ITEMS |  |  | COMPLETED | 2016-05-27 | Rahul B
4 | SPRINT EXECUTION
| SPRINT 1 | 2016-05-28 | 2016-05-31 | COMPLETED | 2016-05-31
| DEVELOP_WORK_ITEM |  |  | COMPLETED | 2016-06-02 | Amit Sharma, Naveen, Manish
| CREATE JUNITS |  |  | COMPLETED | 2016-06-02 | Amit Sharma
| CREATE UI Unit Test Case |  |  | COMPLETED | 2016-06-02 | Manish
| PERFORM UNIT TESTING |  |  | COMPLETED | 2016-06-02 | Amit Sharma, Manish
| PERFORM CODE REVIEW |  |  | COMPLETED | 2016-06-02 | Vishal
| CREATE AUTOMATION SYSTEM TEST CASE |  |  | COMPLETED | 2016-06-02 | Vivek
| CODE CHECKIN |  |  | COMPLETED | 2016-06-02 | Amit Sharma, Manish
| AUTO BUILD |  |  | COMPLETED | 2016-06-02 | Brijesh
| DEPLOY TO QA SERVER |  |  |  |  | Brijesh
| SPRINT REVIEW |  |  | COMPLETED | 2016-05-31 | Rahul B, Amit Sikka
| SPRINT CLOSE |  |  | COMPLETED
| SPRINT 2 | 2016-06-01 | 2016-06-04
| DEVELOP_WORK_ITEM |  |  | COMPLETED | 2016-06-04 | Amit Sharma, Naveen, Manish
| CREATE JUNITS |  |  | COMPLETED | 2016-06-04 | Amit Sharma
| CREATE UI Unit Test Case |  |  | COMPLETED | 2016-06-04 | Manish
| PERFORM CODE REVIEW |  |  | COMPLETED | 2016-06-06 | Vishal
| PERFORM UNIT TESTING |  |  | COMPLETED | 2016-06-06 | Amit Sharma, Manish
| CREATE AUTOMATION SYSTEM TEST CASE |  |  | COMPLETED | 2016-06-05 | Vivek
| EXECUTE AUTOMATION SYSTEM TEST CASE |  |  | In Progress |  | Vivek
| CODE CHECKIN |  |  | COMPLETED | 2016-06-06 | Amit Sharma, Manish
| BUILD |  |  | COMPLETED | 2016-06-06 | Brijesh
| DEPLOY TO QA SERVER |  |  | In Progress |  | Brijesh
| SPRINT REVIEW |  |  | COMPLETED | 2016-06-04 | Rahul B, Amit Sikka
SPRINT CLOSE
5 | STABILIZATION
| BUG FIXING | 2016-06-05 | 2016-06-07 | In Progress |  | Amit Sharma, Manish, Rahul B, Vishal
| REGRESSION TEST CASE EXECUTION | 2016-06-08 | 2016-06-08 | In Progress |  | Vivek
CODE FREEZE
6 | UAT | 2016-06-08 | 2016-06-08 |  |  | Rahul B , Vaibhav, Amit Sikka
7 | BUG FIXING | 2016-06-08 | 2016-06-08 |  |  | Amit Sharma , Manish
8 | Documentation | 2016-06-05 | 2016-06-07 | COMPLETED | 2016-06-06 | Veenus
9 | GO NOGO | 2016-06-08 | 2016-06-08 |  |  | Amit Sikka
10 | CODE FREEZE GITHUB REPOSITORY | 2016-06-09 | 2016-06-09 |  |  | Amit Sharma, Vishal